## Pipeline
Title | Description | New Contract Reference | Value | Category | Service Area | Directorate | PLANNED Advert Dispatch Date | PLANNED Tender Return Date | PLANNED Award Date | PLANNED Contract Start
High Level Street Design Feasibility Software | Procurement of an intuitive, existing software tool that will enable policy staff and decision-makers as well as engineers to propose and explore different options for allocating roadspace. - Client to vary the end date as 2 extensions are available. | CA1559 | 70000 | Digital & Technology | Place & Environment Policy | Transport Policy & Delivery | 2022-12-01 | 2023-01-01 | 2023-03-01 | 2025-02-01
M&E Services Contract | M&E Services Contract | CA51855 | 2150000 | Facilities Management | Facilities & Assets | Transport Ops & Passenger Experience | 2024-06-01 | 2024-07-01 | 2024-09-01 | 2024-10-01
Evaluation of Natural Flood Management | Procurement of evaluation services for Natural Flood Management CA's Evaluation Services Framework. |  | 66000 | Professional Services | Research & Intelligence | Strategy, Comms. & Intelligence | 2025-04-01 | 2025-05-01 | 2025-07-01 | 2025-07-01
Car share/Car Club | West Yorkshire and York Car Share Contract for Local Authorities | CA1585 / 53568 | 2500000 | Transport | Transport Policy | Transport Policy & Delivery | 2025-04-01 | 2025-05-01 | 2025-07-01 | 2025-07-01
Stourton Park and Ride | Provision of Stourton Park and Ride Electric Bus service |  | 3500000 | Transport | Mobility Services | Transport Ops & Passenger Experience | 2025-04-01 | 2025-05-01 | 2025-07-01 | 2025-07-01
West Yorkshire Network Navigation Graphic Design | Creation of graphic designs for bus stops and bus shelters | 94872 | 75000 | Built Environment | Transforming Cities Fund | Transport Capital Programme | 2025-06-30 | 2025-07-21 | 2025-08-18 | 2025-09-08
Vehicle and Vehicle Maintenance Advice | requirement for a contract for adhoc advice on areas related to Vehicles and Vehicle Maintenance Advice (A similar contract was previously provided by Logistics UK/Freight Transport Association Services to Undertake routine checks on Bus Operators. Contract is required for for ad-hoc usage. Spend would only occur under this contract if required by the Mobility Services team. |  | 60000 | Transport | Mobility Services | Transport Ops & Passenger Experience | 2025-07-29 | 2025-08-29 | 2025-10-29 | 2025-11-29
Corporate Environmental Plan |  |  | 100000 | Professional Services | Strategy & Corporate Performance | Strategy, Comms. & Intelligence | 2025-07-29 | 2025-08-29 | 2025-10-29 | 2025-11-29
Disability Design Reference Group - creation and management of group | Organisation to support with creating, recruiting to, and managing the new Disability Design Reference Group for transport projects which the Combined Authority is setting up. |  | 450000 | Services | Transport Policy | Transport Policy & Delivery | 2025-07-29 | 2025-08-29 | 2025-10-29 | 2025-11-29
LBA Parkway - ES4 design review |  | CA64779 / CA1254 | 500000 | Built Environment | Transport Implementation | Transport Policy & Delivery | 2025-07-29 | 2025-08-29 | 2025-10-29 | 2025-11-29
LBAP Rail Station - Ground Investigation, Detailed Design, FBC & Planning Applications | Consultancy required to complete the initial package of ground investigations, Detailed Design, completion of the FBC & all planning applications. |  | 2400000 | Civils | Transport Implementation | Transport Policy & Delivery | 2025-07-29 | 2025-08-29 | 2025-10-29 | 2025-11-29
Portfolio Management & Appraisal Services Framework | qualified and experienced consultant/s to provide advice and support in the appraisal and assurance of scheme project business cases that progress through its local Assurance Framework. Consultants seeking to be appointed to this commission will be expected to demonstrate a breadth of skills and expertise which reflects the broad range of projects that come forward to the Combined Authority for funding, including transport, housing, regeneration, economic development, and flood resilience. | 72922 | 800000 | Professional Services | Portfolio Mgt & Appraisal | Strategy, Comms. & Intelligence | 2025-08-01 | 2025-09-01 | 2025-11-01 | 2025-12-01
VCSE Trailblazer - Bradford | ` |  | 801000 |  | Employment & Skills | Inclusive Economy, Skills & Culture | 2025-08-04 | 2025-09-04 | 2025-11-04 | 2025-12-04
annual public perceptions of transport survey |  | 51229 | 160000 |  | Research & Intelligence | Strategy, Comms. & Intelligence | 2025-08-28 | 2025-09-28 | 2025-11-28 | 2025-12-28
Procurement of an E -learning supplier | E - learning modules and Learning Management System | New tender, previous contract was extended for a year | 75000 |  | HR | Corporate Centre | 2025-08-29 | 2025-09-29 | 2025-11-29 | 2025-06-29
Step-free Station Access ES5-8 | Design and build contract for rail station accessible infrastructure improvement. ES5 as detailed design to be approved by Network Rail and ES6-8 includes construction, sign off and handback to Network Rail. Potentially to also include FBC economic and financial business case support. | N/A | 400000 | Built Environment | Transport Implementation | Transport Policy & Delivery | 2025-08-29 | 2025-09-29 | 2025-11-29 | 2025-12-29
Phase 1 Mobility Hub Component Procurement |  |  | 2500000 | Built Environment | Transport Implementation | Transport Policy & Delivery | 2025-08-29 | 2025-09-29 | 2025-11-29 | 2025-12-29
HDBS Delivery Stage NEC Project Manager & NEC Supervisor | NEC Project Manager & NEC Supervisor | CA80605 | 200000 | Transport | Transport Implementation | Transport Policy & Delivery | 2025-09-01 | 2025-10-01 | 2025-12-01 | 2026-01-01
Property Services Cleaning, Customer Care and Posting of Bus Timetables |  | CA1226 | 2075000.34 | Facilities Management | Facilities & Assets | Transport Ops & Passenger Experience | 2025-09-14 | 2025-10-14 | 2025-12-14 | 2026-01-14
West Yorkshire District Centre Mode Share Counts | Conduct annual survey of the number of people using different means of transportation in West Yorkshire to provide required data for planning sustainable travel within the district. |  | 700000 | Professional Services | Research & Intelligence | Strategy, Comms. & Intelligence | 2025-09-27 | 2025-10-27 | 2025-12-27 | 2026-01-27
Impact Fund - Fund Manager - DO NOT PUBLISH UNTIL CONFIRMED. | Procurement of a Fund Manager to manage the Impact Fund |  | 12000000 | Professional Services | Regeneration | Policing, Environment & Place | 2025-09-30 | 2025-10-31 | 2025-12-31 | 2026-01-31
Elland Railway Station - Enabling Works | We are looking to procure a contractor to deliver some enabling works to allow the Elland Railway Station Scheme to start an approved construction activity before the planning deadline of 27 February 2026. Type of activity has not been agreed yet. |  | 500000 |  | Transport Implementation | Transport Capital Programme | 2025-10-01 | 2025-11-01 | 2025-12-15 | 2025-12-15
Elland Rail Station Stage 2 Contract | Contractor to enter into construction phase of Elland Station Scheme | 51754 | 29000000 |  | Transport Implementation | Transport Capital Programme | 2025-10-01 | 2025-11-01 | 2026-01-01 | 2026-02-01
LBA Parkway Rail Station - GRIP 5-8 Contractor | Construction of LBAP rail station |  | 60000000 | Civils | Transport Implementation | Transport Policy & Delivery | 2025-10-31 | 2025-11-30 | 2026-01-30 | 2026-02-28
Temporary Staffing and Hard to Fill Recruitment Vacancies |  |  | 3000000 | Professional Services | HR | Corporate Centre | 2025-12-01 | 2026-01-01 | 2026-03-01 | 2026-04-01
Electricity Supply | Electricity Supply |  | 10000000 | Facilities Management | Facilities & Assets | Transport Ops & Passenger Experience | 2026-01-01 | 2026-02-01 | 2026-04-01 | 2026-05-01
Leeds Bus Station Roof - Works | Leeds Bus Station Roof - Works |  | 2500000 | Building | Facilities & Assets | Transport Ops & Passenger Experience | 2026-03-01 | 2026-04-01 | 2026-06-01 | 2026-07-01
Depot refurbishment works | Requirement for refurbishment works to depots acquired, or to be acquired by the CA for Bus Franchising. This work will ensure depots confirm to CA requirements, including but not limited to health and safety requirements. Works to be undertaken by current operator some are required before purchase |  | 4000000 | Building | Bus Reform | Transport Policy & Delivery | 2026-04-02 | 2026-05-02 | 2026-07-02 | 2026-08-02
Digital Skills Framework | Setting up a multiple supplier framework in order to train individuals in digital skills across West Yorkshire. | 53161 | 30000000 | Professional Services | Employment & Skills | Inclusive Economy, Skills & Culture | 2026-05-01 | 2026-06-01 | 2026-08-01 | 2026-10-01
Access Bus Re-tender | Re-procurement of Access Bus services |  |  | Transport | Mobility Services | Transport Ops & Passenger Experience | 2026-06-01 | 2026-07-14 | 2026-08-24 | 2027-04-01
SEN Taxis Annual DPS Call-off (2026) | Annual procurement of SEN taxi provision in Wakefield (1 year contracts) DPS Ref 64800. |  | 4000000 | Transport | Mobility Services | Transport Ops & Passenger Experience | 2026-06-12 | 2026-06-26 | 2026-07-17 | 2026-09-02
Bus Franchising - Round 2 - Zone/Lot 1B | Procurement of Franchised Bus Services in West Yorkshire - Wakefield Small Lot. Service details, value and procurement process remain subject to finalisation prior to procurement commencement. |  | 5000000 | Transport | Mobility Services | Transport Ops & Passenger Experience | 2026-07-01 |  | 2027-09-30 | 2027-01-01
Bus Franchising - Round 2 - Zone/Lot 2A | Procurement of Franchised Bus Services in West Yorkshire - Leeds 1 Large Lot. Service details, value and procurement process remain subject to finalisation prior to procurement commencement. |  | 15000000 | Transport | Mobility Services | Transport Ops & Passenger Experience | 2026-07-01 |  | 2027-03-31 | 2028-01-01
Bus Franchising - Round 2 - Zone/Lot 2B | Procurement of Franchised Bus Services in West Yorkshire - Five Towns Large Lot. Service details, value and procurement process remain subject to finalisation prior to procurement commencement. |  | 15000000 | Transport | Mobility Services | Transport Ops & Passenger Experience | 2026-07-01 |  | 2027-03-31 | 2028-01-01
Bus Franchising - Round 2 - Zone/Lot 1A | Procurement of Franchised Bus Services in West Yorkshire - Wakefield Large Lot. Service details, value and procurement process remain subject to finalisation prior to procurement commencement. |  | 15000000 | Transport | Mobility Services | Transport Ops & Passenger Experience | 2026-07-01 |  | 2027-03-31 | 2028-01-01
Bus Franchising - Round 2 - Zone/Lot 2B | Procurement of Franchised Bus Services in West Yorkshire - Leeds 1 Small Lot. Service details, value and procurement process remain subject to finalisation prior to procurement commencement. |  | 5000000 | Transport | Mobility Services | Transport Ops & Passenger Experience | 2027-01-01 |  | 2027-03-31 | 2028-07-01
Bus Franchising - Round 3 - Zone/Lot 1B | Procurement of Franchised Bus Services in West Yorkshire - Bradford Small Lot. Service details, value and procurement process remain subject to finalisation prior to procurement commencement. |  | 5000000 | Transport | Mobility Services | Transport Ops & Passenger Experience | 2027-04-01 |  | 2027-06-30 | 2027-10-01
Bus Franchising - Round 3 - Zone/Lot 2B | Procurement of Franchised Bus Services in West Yorkshire - Keighley Small Lot. Service details, value and procurement process remain subject to finalisation prior to procurement commencement. |  | 5000000 | Transport | Mobility Services | Transport Ops & Passenger Experience | 2027-04-01 |  | 2027-06-30 | 2027-10-01
Bus Franchising - Round 3 - Zone/Lot 2A | Procurement of Franchised Bus Services in West Yorkshire - Keighley Large Lot. Service details, value and procurement process remain subject to finalisation prior to procurement commencement. |  | 15000000 | Transport | Mobility Services | Transport Ops & Passenger Experience | 2027-04-01 |  | 2027-12-30 | 2028-10-01
Bus Franchising - Round 3 - Zone/Lot 1A | Procurement of Franchised Bus Services in West Yorkshire - Bradford Large Lot. Service details, value and procurement process remain subject to finalisation prior to procurement commencement. |  | 15000000 | Transport | Mobility Services | Transport Ops & Passenger Experience | 2027-04-01 |  | 2027-12-30 | 2028-10-01
Bus Franchising - Round 3 - Zone/Lot 3A | Procurement of Franchised Bus Services in West Yorkshire - Leeds 2 Large Lot. Service details, value and procurement process remain subject to finalisation prior to procurement commencement. |  | 15000000 | Transport | Mobility Services | Transport Ops & Passenger Experience | 2027-04-01 |  | 2027-12-30 | 2028-10-01
Bus Franchising - Round 3 - Zone/Lot 4A | Procurement of Franchised Bus Services in West Yorkshire - Calderdale Large Lot. Service details, value and procurement process remain subject to finalisation prior to procurement commencement. |  | 15000000 | Transport | Mobility Services | Transport Ops & Passenger Experience | 2027-04-01 |  | 2027-12-30 | 2028-10-01
SEN Taxis Annual DPS Call-off (2027) | Annual procurement of SEN taxi provision in Wakefield (1 year contracts) DPS Ref 64800. |  | 4000000 | Transport | Mobility Services | Transport Ops & Passenger Experience | 2027-06-12 | 2027-06-26 | 2027-07-17 | 2027-09-02
Evaluation Services Framework (extension) | Review extension options of Evaluation Services Framework - decide to extend, expire or re-procure. |  | 6500000 | Professional Services | Research & Intelligence | Corporate Centre | 2027-06-28 | 2027-07-14 | 2027-09-08 | 2027-10-28
Bus Franchising - Round 2 - Zone/Lot 3B | Procurement of Franchised Bus Services in West Yorkshire - Five Towns Small Lot. Service details, value and procurement process remain subject to finalisation prior to procurement commencement. |  | 5000000 | Transport | Mobility Services | Transport Ops & Passenger Experience | 2027-07-01 |  | 2027-10-31 | 2028-01-01
Bus Franchising - Round 3 - Zone/Lot 3B | Procurement of Franchised Bus Services in West Yorkshire - Leeds 2 Small Lot. Service details, value and procurement process remain subject to finalisation prior to procurement commencement. |  | 5000000 | Transport | Mobility Services | Transport Ops & Passenger Experience | 2027-10-01 |  | 2027-12-30 | 2028-04-01
FE Course Providers for Adult Education Budget (DPS Stage 1) |  | CA1310 | 20000000 | Professional Services | Employment & Skills | Inclusive Economy, Skills & Culture | 2028-04-01 | 2028-05-01 | 2028-07-01 | 2028-08-01
Bus Franchising - Round 3 - Zone/Lot 4B | Procurement of Franchised Bus Services in West Yorkshire - Calderdale Small Lot. Service details, value and procurement process remain subject to finalisation prior to procurement commencement. |  | 5000000 | Transport | Mobility Services | Transport Ops & Passenger Experience | 2028-04-01 |  | 2027-12-30 | 2028-10-01
SEN Taxis Annual DPS Call-off (2028) | Annual procurement of SEN taxi provision in Wakefield (1 year contracts) DPS Ref 64800. |  | 4000000 | Transport | Mobility Services | Transport Ops & Passenger Experience | 2028-06-11 | 2028-06-25 | 2028-07-16 | 2028-09-01
SEN Taxis DPS | Dynamic Purchasing System for procurement of annual SEN Taxi provision in Wakefield. Current DPS Ref 64800. |  | 28000000 | Transport | Mobility Services | Transport Ops & Passenger Experience | 2029-02-15 | 2029-03-15 | 2029-06-01 | 2029-07-01
Framework Establishment: Real Time Information System | Provision of an Advanced Yorkshire & Humber Real Time Information System and associated services to the Combined Authority (the Services) | PROJECT CA1429 | 5000000 | Digital & Technology | Digital & Technology Services | Corporate Centre | 2031-09-01 | 2031-10-01 | 2031-12-01 | 2032-01-01
Tendered Bus Services Expiring August 2025 | Various tendered bus services requiring extension and/or re-tender. See comments before allocation. | N/A | 60000 | Transport | Mobility Services | Transport Ops & Passenger Experience |  |  |  | 2025-09-01
Business Database Information | Database of business information |  | 60000 | Professional Services | Marketing & Campaigns | Strategy, Comms. & Intelligence
Urban Traffic Management Control Monitoring and Evaluation | Consultant for monitoring and evaluation of existing traffic management control programme. |  | 79000 | Professional Services | Transport Policy | Transport Policy & Delivery
Social Value Management Software | Platform to manage, record, and report on social value delivered on contracts awarded by WYCA |  | 120000 | Digital & Technology | Commercial | Corporate Centre
Tendered Bus Services Expiring April 2026 | Various tendered bus services requiring extension and/or re-tender. See comments before allocation. | N/A | 150000 | Transport | Mobility Services | Transport Ops & Passenger Experience |  |  |  | 2026-05-01
Vehicle disposal/auction supplier | Procurement for supplier to auction/sell/recycle/dipose vehicles that are no longer needed as part of the AccessBus Fleet owned by the CA (which new vehicles are currently being re-procured for). Extension options may be included for disposals of fleet further in the future, particularly given the CA will be owning much more Fleet in future as part of Bus Franchising. |  | 250000 | Fleet | Mobility Services | Transport Ops & Passenger Experience |  |  |  | 2025-10-01
Waste Disposal - Wellington House and Bus Stations | Provision of waste management services. | CA1459 | 330000 | Facilities Management | Facilities & Assets | Transport Ops & Passenger Experience
Schedulling software | Software needed going into a franchised world where we need to specify timetables and potentially bus workings for operators. We would also want to be able to carry out modelling on the bus network and look at assumed costs of changes to the network. |  | 500000 | Digital & Technology | Bus Reform | Bus Franchising
Bus Franchising Customer Workstream Support (Phase 3) | Procurement of professional services/consultancy support for the Customer Workstream. Phase 3 work expected to be longer term contract than Phase 1 and 2, and is anticipated to focus on the CA's long term customer proposition for franchising. |  | 1000000 | Professional Services | Bus Reform | Transport Policy & Delivery
Tendered Bus Services Expiring September 2026 | Various tendered bus services requiring extension and/or re-tender. See comments before allocation. | N/A | 1100000 | Transport | Mobility Services | Transport Ops & Passenger Experience |  |  |  | 2026-10-01
Tendered Bus Services Expiring October 2025 | Various tendered bus services requiring extension and/or re-tender. See comments before allocation. | N/A | 1300000 | Transport | Mobility Services | Transport Ops & Passenger Experience |  |  |  | 2025-11-01
HEWY Low Interest Loan (Revolving) | Partner to support the operation and management of a low interest loan pot for residential efficiency development | 94158 | 1500000 | Professional Services | Place & Environment Policy | Policing, Environment & Place
SEN Taxis Annual DPS Call-off (2029) | Annual procurement of SEN taxi provision in Wakefield (1 year contracts) DPS Ref 64800. |  | 4000000 | Transport | Mobility Services | Transport Ops & Passenger Experience
Maintenance and Repair of On-street Infrastructure | Provision of on-street new infrastructure which will include new shelters and bus stops, in addition to ongoing maintenance and repair works to existing stock consisting of circa 4,000 shelters and 10,000 bus stops. | CA53197 | 10000000 | Built Environment | Facilities & Assets | Transport Ops & Passenger Experience
Huddersfield Bus Station Construction | Contract Phase Two excluding Kirklees Canopy works | 85564 | 14000000 | Building | Transforming Cities Fund | Transport Policy & Delivery
Mass Transit Delivery Packages | Mass Transit Construction | N/A | 1911760000 | Built Environment | Mass Transit | Mass Transit |  |  |  | 2028-11-01
Mass Transit and Bus Reform Funding and Finance Partner 2 | Financial support for MT and BR programmes |  |  |  | Finance | Finance & Commercial Services
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please amend to 60 Characters or less when transferring from previous tab

## WIP
Title | Description | New Contract Reference | Value | Category | Service | Directorate | PLANNED Advert Dispatch Date | PLANNED Tender Return Date | PLANNED Award Date | PLANNED Contract Start | ACTUAL Advert Dispatch Date | ACTUAL Tender Return Date | ACTUAL Award Date | ACTUAL Contract Start
CRSTS WY Places Procurement for Programme OBC | CRSTS WY Places procurement for programme OBC, following completion of SOC which was direct awarded to Jacobs who are currently working on the scheme | 83442 | 200000 | Built Environment | Transport Implementation | Transport Policy & Delivery | 2024-10-03 | 2024-11-03 | 2024-12-01 | 2024-12-02
ICT Hardware and Software Partner |  | 81062 | 20000000 | Digital & Technology | Digital & Technology Services | Finance & Commercial Services | 2024-11-25 | 2024-12-27 | 2025-03-10 | 2025-04-01
CSM Assessor | Common Safety Method (CSM) support to develop and deliver proposals for a new rail station at Elland, Leeds Bradford, White Rose and Thorpe Park). |  | 552503.66 | Professional Services | Transport Implementation | Transport Policy & Delivery | 2024-12-03 | 2025-01-06 | 2025-02-03 | 2025-02-10
Payment provider | Card payment provider |  | 450000 | Transport | Passenger Experience | Transport Ops & Passenger Experience | 2025-01-15 | 2025-02-01 | 2025-04-01 | 2025-04-01
Mass Transit Independent Competent Person | Appoint an 'independent competent person' (ICP) to help devise a written scheme of verification for the Mass Transit system in compliance with statutory requirements |  | 8000000 | Professional Services | Mass Transit | Mass Transit | 2025-01-01 | 2025-02-01 | 2024-04-01 | 2025-04-01
Small Passenger Buses | Procurement of 40 small passenger buses for the Access Bus Service. |  | 6500000 | Fleet | Mobility Services | Transport Ops & Passenger Experience | 2025-01-06 | 2025-02-06 | 2025-03-16 | 2025-04-01
Public Affairs Agency Brief | The West Yorkshire Combined Authority would like to work with an agency to develop a public affairs campaign that specifically covers an intense period of activity between March and June 2025 to meet our immediate objectives of attempting to align Government to West Yorkshire’s priorities ahead of the Spending Review. | 96788 | 150000 | Services | Mass Transit | Mass Transit | 2025-03-03 | 2025-03-11 | 2025-03-12
Mass Transit Growth Prospectus |  | 95155 | 1200000 | Professional Services | Mass Transit | Mass Transit | 2025-02-23 | 2025-03-15 | 2024-05-15 | 2025-06-01
Communities, Consultation & Engagement Framework | Looking to set up a framework agreement to help us commission support with C&E activities inc analysis and reporting | 93539 | 500000 |  | Marketing & Campaigns | Strategy, Comms. & Intelligence | 2025-02-17 | 2025-03-17 | 2025-05-17 | 2025-06-01
School Bus Contracts ending on 31 August 2025 | School Transport services for re-tendering. Commencement of services 01/09/25.. | N/A | 47500000 | Transport | Mobility Services | Transport Ops & Passenger Experience | 2025-02-14 | 2025-03-21 | 2025-06-01 | 2025-09-01 | 2025-02-14
Public Transport Data Management System (COSA) |  | 85504 | 1800000 | Digital & Technology |  | Transport Ops & Passenger Experience | 2025-02-17 | 2025-03-24 | 2025-05-01 | 2025-05-15
Skills Bootcamps Wave 6 provision | Adult skills training courses for West Yorkshire residents | 92225 | 6000000 | Learning & Development | Employment & Skills | Inclusive Economy, Skills & Culture | 2025-02-28 | 2025-03-28 | 2025-04-30 | 2025-06-01 | 2025-03-17 | 2025-04-10
Thorpe Park Rail Station - Car Park | Development of a car park at Thorpe Park rail station | 52894 | 3500000 | Civils | Transport Implementation | Transport Policy & Delivery | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01
Provision of Treasury, Borrowing, Investment & Cash Management | Reassessment of the provision of Treasury, Borrowing, Investment & Cash Management Services | N/a | 92000 |  | Finance | Corporate Centre | 2025-04-04 | 2025-04-04 | 2025-05-09 | 2025-05-16
Wide Area Network (WAN) Refresh | Wide Area Network | PROJECT CA1230 | 350000 | Digital & Technology | Digital & Technology Services | Corporate Centre | 2025-03-07 | 2025-04-11 | 2025-06-01 | 2025-07-01
Mass Transit Environmental Partner 2 | Environmental Partner to support the ongoing Mass Transit Programme | 87599 | 7500000 | Professional Services | Mass Transit | Mass Transit | 2025-03-12 | 2025-04-11 | 2025-05-07 | 2025-06-01
Real-Time Passenger Information Battery Powered Displays | Provision of Real-Time Passenger Information Battery Powered Displays for Bus Stop Pole and Shelters | PROJECT CA1088 | 10000000 | Digital & Technology | Transport Policy | Transport Policy & Delivery | 2025-03-07 | 2025-04-11 | 2025-05-09 | 2025-07-01
Estate Management and Valuation Services Contract | Estate management service relating to portfolio of properties, land and assets and located in the five districts of West Yorkshire. | 92148 | 4000000 | Facilities Management | Facilities & Assets | Transport Ops & Passenger Experience | 2025-03-17 | 2025-04-17 | 2025-05-19 | 2025-06-01
Langthwaite EZ - Vacant Site Management Services | Vacant site management services including developing a strategy for ensuring health and safety | 95465 | 150000 | Built Environment | Economic Implementation | Policing, Environment & Place | 2025-04-17 | 2025-05-01 | 2025-05-08 | 2025-05-15 | 2025-04-16
Bradford Interchange Condition Surveys and Strategic Support | Ongoing condition surveys at Bradford Interchange and strategic support delivered to assist in establishing life expectancy of the assets | 96885 | 100000 | Built Environment | Transforming Cities Fund | Transport Capital Programme | 2025-04-23 | 2025-05-02 | 2025-05-08 | 2025-05-14 | 2025-04-23
Local Transport Plan statutory consultation analysis and support | Consultation feedback analysis, consultation event support. | n/a | 120000 |  | Transport Policy | Transport Policy & Delivery | 2025-04-18 | 2025-05-02 | 2025-05-19 | 2025-06-02
Property Condition Surveys | services | 97463 | 120000 |  | Facilities & Assets | Transport Ops & Passenger Experience | 2025-04-02 | 2025-05-09 | 2025-06-03 | 2025-06-09 | 2025-04-02
West Yorkshire Perpetrator Contract | The programme will focus on first time, standard level perpetrators of domestic abuse who receive a conditional caution. The programme will be open to those perpetrators aged over 16 only. The successful provider must enable programme access to perpetrators across West Yorkshire. |  | 400000 | Professional Services | Policing & Crime | Policing, Environment & Place | 2025-04-14 | 2025-05-09 | 2025-06-09 | 2025-06-16
Commercial Consultant for Housing & Regeneration Programmes | To procure Commercial advice for Housing / Regeneration programmes. | 95769 | 3500000 | Professional Services | Regeneration | Policing, Environment & Place | 2025-04-07 | 2025-05-09 | 2025-06-10 | 2025-06-12
Free Courses for Jobs | Free Courses For Jobs- contract to start 1st August 2025 |  | 2000000 |  | Employment & Skills | Inclusive Economy, Skills & Culture | 2025-04-14 | 2025-05-12 | 2025-07-18 | 2025-07-25
Step-free Station Access - ES4 Design | Designer consultancy support to develop an ES3 Option Selection Report up to ES4 design to be approved by Network Rail | 94248 | 170000 | Built Environment | Transport Implementation | Transport Policy & Delivery | 2025-04-02 | 2025-05-14 | 2025-06-12 | 2025-06-26 | 2025-04-02
West Yorkshire Online Panel |  |  | 100000 |  | Transport Policy | Transport Policy & Delivery | 2025-04-16 | 2025-05-16 | 2025-07-16 | 2025-08-16
Staff training requirements- L&D Framework | E-Learning modules |  | 3000000 | Learning & Development | HR | Corporate Centre | 2025-04-18 | 2025-05-16 | 2025-06-13 | 2025-06-27
MCard marketing tender 2025 | Marketing and comms | 98651 | 350000 | Professional Services | Marketing & Campaigns | Strategy, Comms. & Intelligence | 2025-05-09 | 2025-05-23 | 2025-06-20 | 2025-07-01
WY Victims Referral, Assessment and Local Support Services | Referral, Assessment and Local Support Services for WY | 98478 | 8400000 | Professional Services | Place & Environment Policy | Policing, Environment & Place | 2025-04-30 | 2025-05-30 | 2025-07-31 | 2025-10-01 | 2025-04-30 | 2025-05-30
Regional Heritage Guide | Development of a guide that will ensure consistency and robustness of approach in balancing the needs of retrofit against planning/heritage considerations. |  | 80000 | Professional Services |  | Policing, Environment & Place | 2025-05-19 | 2025-05-30 | 2025-06-16 | 2025-06-30
Due Diligence Partner for Financial Assurance |  |  | 150000 | Professional Services | Business Innovation Skills & Culture Policy | Finance & Commercial Services | 2025-05-05 | 2025-06-05 | 2025-08-05 | 2025-09-05
Marketing & Communications Framework (re-tender) | Provision of Marketing and Communications Services |  | 2000000 | Communications | Marketing & Campaigns | Strategy, Comms. & Intelligence | 2025-05-08 | 2025-06-05 | 2025-08-06 | 2025-09-06
Independent Sexual Violence Advocacy Services/s |  |  | 432000 | Professional Services | Policing & Crime | Policing, Environment & Place | 2025-05-09 | 2025-06-08 | 2025-08-01 | 2025-10-01
Dewsbury Line Transport Study | Transport Study for the Mass Transit System in West Yorkshire |  | 150000 | Built Environment | Mass Transit | Mass Transit | 2025-05-14 | 2025-06-11 | 2025-07-09 | 2025-07-30
Legal Consultant for Housing & Regeneration Programmes | To procure Legal advice for Housing / Regeneration programmes. | 95770 | 3000000 | Professional Services | Regeneration | Policing, Environment & Place | 2025-05-14 | 2025-06-11 | 2025-07-11 | 2025-07-21
Early Stage Investment Fund Partner | We are looking for an Investment Fund Manager with experience in early-stage investments into Health & Life Science and Digital Tech companies across West Yorkshire. |  | 15000000 | Professional Services | Trade & Investment | Inclusive Economy, Skills & Culture | 2025-05-22 | 2025-06-11 | 2025-07-07 | 2025-07-28
Infrastructure for Charging Stations | Procurement for EV Charging stations across various depots for the ZEB Team using CRSTS Funding |  | 8000000 | Built Environment | Bus Reform | Transport Policy & Delivery | 2025-05-15 | 2025-06-15 | 2025-07-15 | 2025-08-01
SEN Taxis Annual DPS Call-off (2025) | Annual procurement of SEN taxi provision in Wakefield (1 year contracts) DPS Ref 64800. | 98092 | 4500000 | Transport | Mobility Services | Transport Ops & Passenger Experience | 2025-06-12 | 2025-06-26 | 2025-07-17 | 2025-09-02
Automatic Doors: Maintenance, Repair and Replacement |  |  | 4000000 | Facilities Management | Facilities & Assets | Transport Ops & Passenger Experience | 2025-06-01 | 2025-07-01 | 2025-09-01 | 2025-10-01
Connect to Work Programme (Work and Health) | A programme to support people who have health conditions or disabilities, into work. |  | 48500000 | Professional Services | Employment & Skills | Inclusive Economy, Skills & Culture | 2025-06-01 | 2025-07-01 | 2025-08-15 | 2025-09-02
Adult Cycle Training 2025 | 49201. The Combined Authority has offered adult cycle training through a range of different programmes since 2016, and now wish to build on what has already been delivered. We are looking to work with an organisation who will co-ordinate and manage adult cycle training provision across West Yorkshire, working in collaboration with local authority district partners, local cycle training providers and local instructors. The successful tenderer will be able to show experience of having delivered adult cycle training programmes previously, an ability to collaborate with training providers and local authority partners across West Yorkshire, and to resource this work through appropriate staffing. The successful tenderer will also work with the Combined Authority and its partners to co-ordinate delivery of this work alongside other interventions. | 98725 | 714050 | Built Environment | Transport Implementation | Transport Capital Programme | 2025-06-02 | 2025-07-02 | 2025-07-16 | 2025-08-04
West Yorkshire Creative Health System | Establishing a WY Creative Health System: research and mapping, programme co-design, advocacy, group membership management, bid writing. |  | 940000 | Professional Services | Business Innovation Skills & Culture Policy | Inclusive Economy, Skills & Culture | 2025-05-19 | 2025-07-11 | 2025-09-05 | 2025-10-01
Strategic Development Partner 4 | A multi-lot framework to deliver strategic development support for transport and associated programmes | 95777 | 20000000 | Professional Services | Transport Implementation | Transport Policy & Delivery | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01
Vehicles for Bus Franchising | Procurement of 1000 buses for bus reform - possibly now to include ZEB and CRSTS |  | 270000000 | Fleet | Bus Reform | Transport Policy & Delivery | 2025-07-21 | 2025-08-21 | 2025-10-05 | 2025-10-19
Corporate Environmental Plan |  |  | 100000 | Professional Services | Strategy & Corporate Performance | Strategy, Comms. & Intelligence | 2025-07-29 | 2025-08-29 | 2025-10-29 | 2025-11-29
Leeds Area-Based Scheme Detailed Design | We are seeking to procure a detailed design study, which will help inform the development of a business case to secure funding to deliver Part 2 of the Leeds Area-Based scheme. |  | 100000 |  | Economic Implementation | Policing, Environment & Place | 2025-07-30 | 2025-08-30 | 2025-10-30 | 2025-05-30
Combined Authority Technology Strategy Assurance Partner | To provide external assurance and ad hoc advice during the implementaiton of the Future Technology Strategy | n/a | 130000 | Digital & Technology | ICT | Corporate Centre | 2025-07-30 | 2025-08-30 | 2025-10-30 | 2025-11-30
annual public perceptions of transport survey |  | 51229 | 160000 |  | Research & Intelligence | Strategy, Comms. & Intelligence | 2025-08-28 | 2025-09-28 | 2025-11-28 | 2025-12-28
Bus Franchising - Round 1 - Zone/Lot 1A | Procurement of Franchised Bus Services in West Yorkshire - Leeds 3 Large Lot. Service details, value and procurement process remain subject to finalisation prior to procurement commencement. |  | 15000000 | Transport | Mobility Services | Transport Ops & Passenger Experience | 2025-10-01 | 2025-12-01 | 2026-06-30 | 2027-04-01
Bus Franchising - Round 1 - Zone/Lot 3B | Procurement of Franchised Bus Services in West Yorkshire - Kirklees Small Lot. Service details, value and procurement process remain subject to finalisation prior to procurement commencement. |  | 5000000 | Transport | Mobility Services | Transport Ops & Passenger Experience | 2026-10-01 | 2026-10-31 | 2026-12-31 | 2027-04-01
Wakefield Bus Depot | Procurement strategy for design and build, and possibly own, operate and transfer |  | 30000000 | Built Environment | Bus Reform | Bus Franchising | 2028-05-01 | 2028-06-01 | 2028-08-01 | 2028-09-01
Create Growth Programme | Skills and business support for the creative industries. | 78219 (for Create Growth Programme 2024/25). . | 318750 |  | Business Innovation Skills & Culture Policy | Inclusive Economy, Skills & Culture
Huddersfield Bus Station Building Control Principal Designer |  |  | 60000 | Professional Services | Transport Implementation | Transport Policy & Delivery
Banking Services contract | Banking services including, treasury management (cash management/overdraft facilities); Payment solutions (BACS/CHAPS/Faster payment; direct debts and standing orders; procurement cards); account management and statement services; fraud protection and security; advice and compliance; digital banking solutions | N/A | 70000 |  | Finance | Corporate Centre |  |  |  | 2025-04-01
Biodiversity Net Gain (BNG) Ecological Support | Ecological support for BNG delivery, including calling off various tasks such as monitoring reports, spot checks etc. |  | 100000 | Professional Services | Place & Environment Policy | Policing, Environment & Place |  |  |  | 2025-06-16
Transport Accessibility Tool | A continuation or replacement of our Basemap licence which expires early June 2025 | CA49132 | 120000 | Transport | Research & Intelligence | Corporate Centre
Social Media Management Tool |  | n/a | 150000 | Digital & Technology | Media | Strategy, Comms. & Intelligence |  |  |  | 2025-04-05
Printing and Distribution of Bus Timetables | Printing and distribution of individual timetables for West Yorkshire buses |  | 180000 | Transport | Passenger Experience | Transport Ops & Passenger Experience
Electronic Document Management System (EDMS) Procurement | EDMS software as a service contract | None | 330000 |  | Transport Capital Programme | Mass Transit |  |  |  | 2025-05-12
Portfolio Information Management System (Development) | A supplier to develop the existing Portfolio Information Management System (PIMS) - or dependent on outcome of discussions, a new system to replace it. |  | 600000 | Digital & Technology | Portfolio Mgmt & Appraisal | Corporate Centre
Smartcard Production 2025 | Production and delivery of ENCTS, MCard and Education travel smartcards to ITSO standards | CA1498 | 975000 | Transport | Transport Policy | Transport Ops & Passenger Experience
Bus Franchising - Round 1 - Zone/Lot 1B | Procurement of Franchised Bus Services in West Yorkshire - Leeds 3 Small Lot. Service details, value and procurement process remain subject to finalisation prior to procurement commencement. |  | 5000000 | Transport | Mobility Services | Transport Ops & Passenger Experience | 2025-10-01 |  | 2025-12-31 | 2026-04-01
Bus Franchising - Round 1 - Zone/Lot 2B | Procurement of Franchised Bus Services in West Yorkshire - Heavy Woolen Small Lot. Service details, value and procurement process remain subject to finalisation prior to procurement commencement. |  | 5000000 | Transport | Mobility Services | Transport Ops & Passenger Experience | 2026-04-01 |  | 2026-06-30 | 2027-10-01
Bus Franchising - Round 1 - Zone/Lot 2A | Procurement of Franchised Bus Services in West Yorkshire - Heavy Woolen Large Lot. Service details, value and procurement process remain subject to finalisation prior to procurement commencement. |  | 15000000 | Transport | Mobility Services | Transport Ops & Passenger Experience | 2025-10-01 |  | 2026-06-30 | 2027-04-01
Bus Franchising - Round 1 - Zone/Lot 3A | Procurement of Franchised Bus Services in West Yorkshire - Kirklees Large Lot. Service details, value and procurement process remain subject to finalisation prior to procurement commencement. |  | 15000000 | Transport | Mobility Services | Transport Ops & Passenger Experience | 2025-10-01 |  | 2026-06-30 | 2027-04-01